## Sheet1
Task | Start Date | No. of Days
Wireframe for the Front-End | 20th Aug | 7
Application Architecture (Design Phase) | 27th Aug | 10
Basic JSP application with MVC | 6th Sep | 7
Incorporating suggestions and feedback | 13th Sep | 7
Elastic Search Integration | 20th Sep | 14
Adding advanced features | 4th Oct | 22
Incorporating suggestions and feedback | 26th Oct | 13
Final Testing | 8th Nov | 7